## 项目
|  | 项目名称: |  | 病虫测报管理平台二期
项目详细
| 开始日期 |  | 开发者 | 尹升日，张忠昱，肖娜娜，刘俊宏，史瑞丰
| 开发时间 |  | 管理者 | 柳哲进
文档记录
No | 日期 | 内容 |  |  | 记录人
1 | 2015-02-28 | 网站和手机端功能进度 |  |  | 尹升日
2

## 周期表
项目进度表 |  | 沈阳德铭源科技 damytech @ 2015 | [7 empty] | 0
项目: | 病虫测报管理平台二期
[6 empty] | 今天: | 2015-04-01 |  |  | Wednesday
(vertical red line)
| 项目管理者: | 柳哲进 | [246 empty] | [42]
| 开始日期: | 2015-03-01 |  | Sunday
| 结束日期: | 2015-03-28 |  | Saturday
[42] | [8 empty] | 周一 (星期一:2): | 2 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 | 2015-03-07 | 2015-03-08 | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-03-14 | 2015-03-15 | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-03-21 | 2015-03-22 | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 | 2015-03-28 | 2015-03-29 | 2015-03-30 | 2015-03-31 | 2015-04-01 | 2015-04-02 | 2015-04-03 | 2015-04-04 | 2015-04-05 | 2015-04-06 | 2015-04-07 | 2015-04-08 | 2015-04-09 | 2015-04-10 | 2015-04-11 | 2015-04-12 | 2015-04-13 | 2015-04-14 | 2015-04-15 | 2015-04-16 | 2015-04-17 | 2015-04-18 | 2015-04-19 | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | 2015-05-02 | 2015-05-03 | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | 2015-05-09 | 2015-05-10 | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15 | 2015-05-16 | 2015-05-17 | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-23 | 2015-05-24 | 2015-05-25 | 2015-05-26 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2015-05-30 | 2015-05-31 | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-06 | 2015-06-07 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-13 | 2015-06-14 | 2015-06-15 | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-04 | 2015-07-05 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10 | 2015-07-11 | 2015-07-12 | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17 | 2015-07-18 | 2015-07-19 | 2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-25 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-01 | 2015-08-02 | 2015-08-03 | 2015-08-04 | 2015-08-05 | 2015-08-06 | 2015-08-07 | 2015-08-08 | 2015-08-09 | 2015-08-10 | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-15 | 2015-08-16 | 2015-08-17 | 2015-08-18 | 2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-22 | 2015-08-23 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-29 | 2015-08-30 | 2015-08-31 | 2015-09-01 | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-24 | 2015-10-25
WBS | 任务 | 开发者 | 开始日期 | 结束日期 | 时间 (天) | % 完成 | 工作时间 | 完成时间 | 剩下日期 | 2: 难度; 2015-03-02: 2015-03-02; 2015-03-09: 2015-03-09; 2015-03-16: 2015-03-16; 2015-03-23: 2015-03-23; 2015-03-30: 2015-03-30; 2015-04-06: 2015-04-06; 2015-04-13: 2015-04-13; 2015-04-20: 2015-04-20; 2015-04-27: 2015-04-27; 2015-05-04: 2015-05-04; 2015-05-11: 2015-05-11; 2015-05-18: 2015-05-18; 2015-05-25: 2015-05-25; 2015-06-01: 2015-06-01; 2015-06-08: 2015-06-08; 2015-06-15: 2015-06-15; 2015-06-22: 2015-06-22; 2015-06-29: 2015-06-29; 2015-07-06: 2015-07-06; 2015-07-13: 2015-07-13; 2015-07-20: 2015-07-20; 2015-07-27: 2015-07-27; 2015-08-03: 2015-08-03; 2015-08-10: 2015-08-10; 2015-08-17: 2015-08-17; 2015-08-24: 2015-08-24; 2015-08-31: 2015-08-31; 2015-09-07: 2015-09-07; 2015-09-14: 2015-09-14; 2015-09-21: 2015-09-21; 2015-09-28: 2015-09-28; 2015-10-05: 2015-10-05; 2015-10-12: 2015-10-12; 2015-10-19: 2015-10-19
1 | 后台网站开发 | 全部 | 2015-03-01 | 2015-03-19 | 19 | 100% | 14 | 19 | 0 | 2: 100
1.1 | 病虫管理 |  | 2015-03-01 | 2015-03-08 | 8 | 100% | 5 | 8 | 0 | 2: 100
1.1.1 | 病虫害信息主页面 | 肖娜娜 | 2015-03-02 | 2015-03-03 | 2 | 100% | 2 | 2 | 0 | 2: 100
1.1.2 | 新增病虫害 | 肖娜娜 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.1.3 | 新增病虫害(调用官方病虫害数据) | 肖娜娜 | 2015-03-05 | 2015-03-07 | 3 | 100% | 2 | 3 | 0 | 2: 100
1.1.4 | 测报表格主页面 | 肖娜娜 | 2015-03-08 | 2015-03-09 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.2 | 测报点管理 |  | 2015-03-01 | 2015-03-07 | 7 | 100% | 5 | 7 | 0 | 2: 100
1.2.1 | 主页面 | 史瑞丰 | 2015-03-01 | 2015-03-02 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.2.2 | 新增测报点 | 史瑞丰 | 2015-03-03 | 2015-03-04 | 2 | 100% | 2 | 2 | 0 | 2: 100
1.2.3 | 批量导出测报点 | 史瑞丰 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.4 | 批量导入测报点 | 史瑞丰 | 2015-03-06 | 2015-03-06 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.5 | 测报点查看/修改/删除，批量删除 | 史瑞丰 | 2015-03-07 | 2015-03-07 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3 | 上报数据管理 |  | 2015-03-01 | 2015-03-12 | 12 | 100% | 9 | 12 | 0 | 2: 130
1.3.1 | 主页面 | 刘俊宏 | 2015-03-01 | 2015-03-03 | 3 | 100% | 2 | 3 | 0 | 2: 130
1.3.2 | 查看、审核上报数据 | 刘俊宏 | 2015-03-04 | 2015-03-06 | 3 | 100% | 3 | 3 | 0 | 2: 130
1.3.3 | 修改上报数据 | 刘俊宏 | 2015-03-07 | 2015-03-08 | 2 | 100% | 0 | 2 | 0 | 2: 130
1.3.4 | 批量导出上报数据 | 刘俊宏 | 2015-03-09 | 2015-03-10 | 2 | 100% | 2 | 2 | 0 | 2: 130
1.3.5 | 导入上报数据 | 刘俊宏 | 2015-03-11 | 2015-03-12 | 2 | 100% | 2 | 2 | 0 | 2: 130
1.4 | 统计分析 |  | 2015-03-09 | 2015-03-14 | 6 | 100% | 5 | 6 | 0 | 2: 100
1.4.1 | 汇总统计 | 肖娜娜 | 2015-03-09 | 2015-03-10 | 2 | 100% | 2 | 2 | 0 | 2: 100
1.4.2 | 折线图统计 | 肖娜娜 | 2015-03-11 | 2015-03-12 | 2 | 100% | 2 | 2 | 0 | 2: 100
1.4.3 | 柱状图统计 | 肖娜娜 | 2015-03-13 | 2015-03-14 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.5 | 工作管理 |  | 2015-03-08 | 2015-03-18 | 11 | 100% | 8 | 11 | 0 | 2: 100
1.5.1 | 测报计划主页面 | 张忠昱，史瑞丰 | 2015-03-08 | 2015-03-09 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.5.2 | 新增、删除测报计划 | 史瑞丰 | 2015-03-10 | 2015-03-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.3 | 编辑测报计划主页面 | 史瑞丰 | 2015-03-11 | 2015-03-12 | 2 | 100% | 2 | 2 | 0 | 2: 100
1.5.4 | 新增工作 | 史瑞丰 | 2015-03-13 | 2015-03-14 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.5.5 | 临时工作 | 张忠昱 | 2015-03-15 | 2015-03-15 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.5.6 | 管理办法 | 张忠昱 | 2015-03-16 | 2015-03-16 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.7 | 上级通知 | 张忠昱 | 2015-03-17 | 2015-03-17 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.8 | 下级通知 | 张忠昱 | 2015-03-18 | 2015-03-18 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.6 | 动态数据 | 史瑞丰 | 2015-03-13 | 2015-03-16 | 4 | 100% | 2 | 4 | 0 | 2: 100
1.7 | 病虫预警 | 肖娜娜 | 2015-03-13 | 2015-03-14 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.8 | 系统设置 |  | 2015-03-01 | 2015-03-19 | 19 | 100% | 14 | 19 | 0 | 2: 100
1.8.1 | 角色设置 | 张忠昱 | 2015-03-01 | 2015-03-02 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.8.2 | 地区管理 | 张忠昱 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.8.3 | 直属单位设置 | 张忠昱 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.8.4 | 用户管理 | 张忠昱 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.8.5 | 字段设置 | 张忠昱 | 2015-03-06 | 2015-03-07 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.8.6 | 表格管理 | 张忠昱 | 2015-03-08 | 2015-03-09 | 2 | 100% | 1 | 2 | 0 | 2: 100
1.8.7 | 系统恢复 | 张忠昱，柳哲进 | 2015-03-15 | 2015-03-19 | 5 | 100% | 4 | 5 | 0 | 2: 100
2 | 安卓手机端开发 | 尹升日 | 2015-03-06 | 2015-03-19 | 14 | 100% | 10 | 14 | 0 | 2: 100
2.1 | 管理员功能 | 尹升日 | 2015-03-06 | 2015-03-14 | 9 | 100% | 6 | 9 | 0 | 2: 100
2.1.1 | 基本信息管理 | 尹升日 | 2015-03-06 | 2015-03-06 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.1.2 | 工作安排 | 尹升日 | 2015-03-07 | 2015-03-07 | 1 | 100% | 0 | 1 | 0 | 2: 100
2.1.3 | 动态数据管理 | 尹升日 | 2015-03-08 | 2015-03-08 | 1 | 100% | 0 | 1 | 0 | 2: 100
2.1.4 | 数据分析 | 尹升日 | 2015-03-09 | 2015-03-09 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.1.5 | 预警信息审核 | 尹升日 | 2015-03-10 | 2015-03-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.1.6 | 视频指导 | 尹升日 | 2015-03-11 | 2015-03-11 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.1.7 | 历史测报数据 | 尹升日 | 2015-03-12 | 2015-03-12 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.1.8 | 测报员管理 | 尹升日 | 2015-03-13 | 2015-03-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.1.9 | 通知 | 尹升日 | 2015-03-14 | 2015-03-14 | 1 | 100% | 0 | 1 | 0 | 2: 100
2.2 | 测报员功能 | 尹升日 | 2015-03-15 | 2015-03-17 | 3 | 100% | 2 | 3 | 0 | 2: 100
2.2.1 | 我的位置 | 尹升日 | 2015-03-15 | 2015-03-15 | 1 | 100% | 0 | 1 | 0 | 2: 100
2.2.2 | 数据上报 | 尹升日 | 2015-03-15 | 2015-03-15 | 1 | 100% | 0 | 1 | 0 | 2: 100
2.2.3 | 我的工作 | 尹升日 | 2015-03-16 | 2015-03-16 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.2.4 | 历史上报查询 | 尹升日 | 2015-03-16 | 2015-03-16 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.2.5 | 视频预约 | 尹升日 | 2015-03-17 | 2015-03-17 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.2.6 | 预警信息申报 | 尹升日 | 2015-03-17 | 2015-03-17 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.2.7 | 测报点管理 | 尹升日 | 2015-03-17 | 2015-03-17 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.2.8 | 测报员管理办法 | 尹升日 | 2015-03-17 | 2015-03-17 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.3 | 设置 | 金学敏 | 2015-03-18 | 2015-03-19 | 2 | 100% | 2 | 2 | 0 | 2: 100
2.3.1 | 我的信息 | 金学敏 | 2015-03-18 | 2015-03-18 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.3.2 | 关于我们，功能介绍 | 金学敏 | 2015-03-18 | 2015-03-18 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.3.3 | 意见反馈 | 金学敏 | 2015-03-19 | 2015-03-19 | 1 | 100% | 1 | 1 | 0 | 2: 100
2.3.4 | 帮助信息 | 金学敏 | 2015-03-19 | 2015-03-19 | 1 | 100% | 1 | 1 | 0 | 2: 100
3 | WebService开发 | 尹升日 | 2015-03-01 | 2015-03-05 | 5 | 100% | 4 | 5 | 0 | 2: 100
3.1 | loginUser(用户登录) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.2 | getShengs(获取省信息) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.3 | getShis(获取市信息) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.4 | getXians(获取县信息) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.5 | getPoints(测报点搜索) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.6 | getPointInfo(获取测报点信息) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.7 | getBlights(病虫害搜索) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.8 | getBlightInfo(获取病虫害信息) | 尹升日 | 2015-03-01 | 2015-03-01 | 1 | 100% | 0 | 1 | 0 | 2: 100
3.9 | getUsers(用户搜索) | 尹升日 | 2015-03-02 | 2015-03-02 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.10 | getUserInfo(获取用户信息) | 尹升日 | 2015-03-02 | 2015-03-02 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.11 | getReports(上报记录搜索) | 尹升日 | 2015-03-02 | 2015-03-02 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.12 | getReportInfo(获取上报信息) | 尹升日 | 2015-03-02 | 2015-03-02 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.13 | getForms(上报表格样式搜索) | 尹升日 | 2015-03-02 | 2015-03-02 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.14 | getFields(表格字段搜索) | 尹升日 | 2015-03-02 | 2015-03-02 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.15 | setReports(病虫害上报) | 尹升日 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.16 | uploadWatcherTrack(测报员轨迹动态上报) | 尹升日 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.17 | uploadExtraTask(发布临时工作) | 尹升日 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.18 | getExtraTasks (获取临时工作) | 尹升日 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.19 | getExtraTaskInfo(获取临时工作信息) | 尹升日 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.20 | getTempBlights(获取新发病虫害) | 尹升日 | 2015-03-03 | 2015-03-03 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.21 | getTempBlightInfo(获取新发病虫害信息) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.22 | uploadTempBlight(新发病虫害申报) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.23 | getHelp(获取管理办法和帮助信息) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.24 | getNotices(获取通知目录) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.25 | getReportLine(获取折线图统计信息) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.26 | getReportBar(获取柱状图统计信息) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.27 | getReportHistory(获取测报点上报记录) | 尹升日 | 2015-03-04 | 2015-03-04 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.28 | getTaskCount(获取测报员工作数量) | 尹升日 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.29 | getTaskList(获取测报员固定工作目录) | 尹升日 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.30 | getTaskInfo(获取固定工作详情信息) | 尹升日 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.31 | getTaskStatus(获取测报员工作结果) | 尹升日 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
3.32 | getVersion(获取版本信息) | 尹升日 | 2015-03-05 | 2015-03-05 | 1 | 100% | 1 | 1 | 0 | 2: 100
4 | 系统测试 |  | 2015-03-16 | 2015-03-22 | 7 | 100% | 5 | 7 | 0 | 2: 100
4.1 | 后台网站测试 | 张忠昱，肖娜娜，刘俊宏，史瑞丰 | 2015-03-16 | 2015-03-17 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.1 | 病虫管理 | 史瑞丰 | 2015-03-16 | 2015-03-17 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.2 | 测报点管理 | 刘俊宏 | 2015-03-16 | 2015-03-17 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.3 | 上报数据管理 | 史瑞丰 | 2015-03-18 | 2015-03-19 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.4 | 统计分析 | 史瑞丰 | 2015-03-16 | 2015-03-17 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.5 | 工作管理 | 刘俊宏 | 2015-03-16 | 2015-03-17 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.6 | 病虫预警 | 史瑞丰 | 2015-03-16 | 2015-03-17 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.1.7 | 系统设置 |  | 2015-03-18 | 2015-03-19 | 2 | 100% | 2 | 2 | 0 | 2: 100
4.2 | 手机端测试 |  | 2015-03-20 | 2015-03-22 | 3 | 100% | 1 | 3 | 0 | 2: 100
4.2.1 | 管理员功能 |  | 2015-03-20 | 2015-03-20 | 1 | 100% | 1 | 1 | 0 | 2: 100
4.2.2 | 测报员功能 |  | 2015-03-21 | 2015-03-21 | 1 | 100% | 0 | 1 | 0 | 2: 100
4.2.3 | 设置 |  | 2015-03-22 | 2015-03-22 | 1 | 100% | 0 | 1 | 0 | 2: 100

## 预算
Budget
Project |  | Project #
Project manager |  | Sponsor | 0
Project artifacts |  | Updated
Budget Status
Approved Budget | Planned Expenditures to Date | Actual Expenditures to Date | Variance
0 | 0 | 0 | 0
| Planned Remaining Budget | Actual Remaining Budget | Variance
| 0 | 0 | 0
Additional $ needed
Budget Details
Internal Expenses
Salaries | Hourly Rate | # Hours | Total Cost
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Other Internal Expenses |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total Internal Expenses |  |  |  | 0
External Expenses
Consulting Costs |  |  | Total Cost
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Capital Expenditures |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total External Expenses |  |  |  | 0
Total Budget |  |  |  | 0

## 风险登记
风险管理 (风险登记)
Project | [8 empty] | Project #
Project manager | [8 empty] | Sponsor | 0
Project artifacts | [8 empty] | Updated
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | What is this risk? | 1 | 2 | 3 | 12 |  | What act or event initiates either the risk occurrence or precipitates the response strategy? | How will you respond to this risk and what actions will you take to match that response? | If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround? | Who monitors this risk?
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
Note on C6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on L6: Options are: Open Closed

## 问题日志
问题日志
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor | 0
Project artifacts |  |  |  | Updated
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | What is the issue? | How will this impact scope, schedule & cost? | How do you intend to deal with this issue? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on F6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## © (hidden)
Gantt Chart Template
© 2008-2009 Vertex42 LLC
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html